## Workflow States
LINEAR WORKFLOW STATES — Issue lifecycle from creation to release
State | Category | Owner | Who Moves It Here | How | Description | SLA | Escalation
Triage | Triage | Product Manager | Anyone | Auto — default for new issues | Newly created issues land here for initial review | — | —
Backlog | Backlog | Product Manager | Product Manager | Manual — during triage/grooming | Triaged but not scheduled for a cycle | — | —
Requirement | Unstarted | Product Manager | Product Manager | Manual — PM picks up from backlog | PM fills in requirements, acceptance criteria, designs | — | Stuck 2+ days → Engg Manager follows up
Todo | Unstarted | Developer (assignee) | Product Manager | Manual — during sprint planning | Fully spec'd, ready for development | — | —
Development | In Development | Developer | Developer | Manual — developer picks it up | Developer is actively working on it | — | —
PR Review | In Development | Reviewer | Auto (GitHub↔Linear) | Auto — PR opened with CRE-xxx | PR is open, awaiting code review. Reviewer owns it. | 1 business day | Stuck 2+ days → Engg Manager
QA | In Development | QA Engineer | Auto (GitHub↔Linear) | Auto — PR merged to develop | Code on develop, auto-deployed to dev. QA owns testing. | 1 business day | Stuck 2+ days → Engg Manager
Pending UAT | In Development | Release Manager | QA Engineer | Manual — QA testing passed | QA testing complete, issue queued for UAT. Release Manager coordinates UAT scheduling with client/stakeholders. | — | —
UAT | In Development | Client / AM | QA / Release Manager | Manual — release branch cut | In release branch, client/stakeholder doing acceptance testing | — | UAT rejected → Engg Manager
Pending Release | Completed | Release Manager | QA / Product | Manual — UAT sign-off received | UAT approved, waiting for production deployment | — | —
Released | Completed | Release Manager | Release Manager | Manual — after prod deployment | Merged to master, tagged, deployed to production. Final state. | — | —
Cancelled | Cancelled | — | Product Manager | Manual | Will not be done; reason documented in issue | — | —
KEY OWNERSHIP RULES
General Principle | At every state, exactly one role owns the issue. That person is responsible for completing their work or moving it forward. If blocked, comment and escalate.
Requirement → PM owns it | PM fills in full requirement details. Issue should NOT move to Todo until PM completes requirements and Dev Lead reviews.
PR Review → Reviewer owns it | Developer must request a specific reviewer. Reviewer is responsible. If changes requested, ownership flips to author until resolved.
QA → QA Engineer owns it | QA must actively monitor issues in this state. Developer's handoff duty: ensure clear acceptance criteria and testing notes.
Self-review not allowed | Every PR needs at least one approval from someone other than the author.
Separate Sheet for TCs

## Test Cases
TEST CASES — Track QA test cases per release
Release Version: | v_._._
Module/Feature Area:
QA Lead:
Test Case ID | Module | Feature | Description | Pre-conditions | Steps | Expected Result | Priority | Status | Tested By | Notes
TC-001 | Auth | Login | Verify user can login with valid credentials | User account exists | 1. Open login page 2. Enter credentials 3. Click Login | User is redirected to dashboard | High
Priority Values: | High
Medium
Low
Critical
Status Values: | Not Tested
Pass
Fail
Blocked
N/A

## Labels & Priority
LINEAR LABELS & PRIORITY — Quick reference for issue tagging
TYPE LABELS (required on every issue)
Label | Color | Use When | Example | Git Branch Prefix
type:feature | Blue | New functionality |  | feature/CRE-xxx-desc
type:bug | Red | Something is broken |  | bugfix/CRE-xxx-desc
type:improvement | Green | Enhancement to existing functionality |  | feature/CRE-xxx-desc
type:chore | Gray | Refactoring, dependency updates, CI changes, docs |  | feature/CRE-xxx-desc
type:hotfix | Orange | Emergency production fix (follows hotfix git flow) |  | hotfix/CRE-xxx-desc
type:tech-debt | Purple | Addressing accumulated technical debt |  | feature/CRE-xxx-desc
PRIORITY (Linear built-in)
Level | Icon | Meaning | Response Time | Examples
Urgent | 🔴 | Production is broken or release is blocked | Immediate | Production crash, data loss, security vulnerability
High | 🟠 | Must be in the next release | Within 1 day | Release-blocker bug, critical client request
Medium | 🟡 | Planned for an upcoming release | Current cycle | Scheduled feature work, planned improvements
Low | 🟢 | Backlog — nice to have | When capacity allows | Minor UI polish, documentation updates
No Priority | ⚪ | Not yet triaged | Needs triage | Newly created issues awaiting review
CLIENT LABELS (required on every issue)
Label | Use When | Tag Pattern | Branch Pattern | Notes
client:shared | Applies to all environments (internal + all clients) | vX.Y.Z | release/vX.Y.Z | Default for most issues
client:<name> | Client-specific work | vX.Y.Z-clientname | release/vX.Y.Z-clientname | Create one label per client
REPOSITORY LABELS - To bet set before PR Review
Label | Repository | Type | Tech Stack | Notes
repo:crego-ai | crego-ai | Backend service | Python, Django | AI/ML capabilities API
repo:crego-flow | crego-flow | Backend service | Python, Django | Flow engine and workflow automation
repo:crego-omni | crego-omni | Backend service | Python, Django, Celery | Core platform API
repo:crego-web | crego-web | Frontend monorepo | React, TypeScript, pnpm | All frontend apps and shared packages
repo:crego-infra | crego-infra | Infrastructure | Kustomize, ArgoCD, Terraform | GitOps K8s, CI/CD
FOUND-IN LABELS (tracks where bugs are discovered)
Label | Environment | Use When | Who Sets It | Notes
found-in:dev | Dev (internal) | Bug discovered during QA/UAT testing on dev environment | QA Engineer | Most bugs should be caught here
found-in:preprod | Pre-prod | Bug discovered during pre-prod testing (release branch) | QA Engineer | Regression or integration bugs
found-in:prod | Production | Bug discovered in production (typically becomes a hotfix) | Developer / Support | Triggers hotfix flow
FLAG LABELS (release management)
Label | Use When | Who Sets It | Who Resolves It | Action Required
release-blocker | Issue blocks the release from going out | QA / Developer | Engg Manager | Must fix before release can proceed
needs-cherry-pick | Fix needs to be applied to another branch | QA / Developer | Developer | Cherry-pick to release or client branch
needs-backport | Fix on release/hotfix branch must go to develop | QA / Release Manager | Developer | Open PR from release branch fix to develop
breaking-change | Introduces a breaking API or behavior change | Developer / Reviewer | Engg Manager | Requires MAJOR version bump, client communication
feature-flag | Behind a feature flag, toggleable per client/env | Developer | Engg Manager | Document flag name and default state

## Release Checklist
RELEASE CHECKLIST — Copy this sheet for each new release
Release Version: | v_._._
Release Date:
Release Manager:
Linear Project Link:
# | Phase | Checklist Item | Owner | Status | Notes
Pre-Release
1 | Pre-Release | All issues in Linear cycle are in 'QA on Dev' or later | QA Lead
2 | Pre-Release | No open 'release-blocker' issues for this version | Release Manager
3 | Pre-Release | All PRs for this release are merged to develop | Dir. of Eng
4 | Pre-Release | All tests pass on develop branch | CI/CD
5 | Pre-Release | Release version number decided (MAJOR.MINOR.PATCH) | Dir. of Eng
6 | Pre-Release | Linear Project created for this release | Release Manager
Cut Release Branch
7 | Cut Release Branch | Release branch created from develop: release/vX.Y.Z | Release Manager
8 | Cut Release Branch | Release branch pushed to GitHub | Release Manager
9 | Cut Release Branch | Pre-prod deployment triggered and verified | DevOps
10 | Cut Release Branch | develop branch is open for next release work | Dir. of Eng
11 | Cut Release Branch | Linear issues moved to 'In Release' state | Release Manager
Pre-prod Testing
12 | Pre-prod Testing | Regression testing completed on pre-prod | QA Lead
13 | Pre-prod Testing | Integration testing completed | QA Lead
14 | Pre-prod Testing | All release-branch bug fixes have 'needs-backport' label | QA Lead
15 | Pre-prod Testing | Bug fixes on release branch backported to develop | Developer
16 | Pre-prod Testing | No open blockers remaining | QA Lead
UAT (Shared Environment)
17 | UAT (Shared Environment) | UAT environment accessible to stakeholders | DevOps
18 | UAT (Shared Environment) | UAT test cases communicated to stakeholders | Release Manager
19 | UAT (Shared Environment) | UAT sign-off received (name and date) | Release Manager
20 | UAT (Shared Environment) | UAT feedback addressed or deferred with agreement | Dir. of Eng
Production Deployment
21 | Production Deployment | Release branch merged to master (merge commit, not squash) | Release Manager
22 | Production Deployment | Tag created on master: vX.Y.Z | Release Manager
23 | Production Deployment | Tag pushed to GitHub, prod deployment triggered | Release Manager
24 | Production Deployment | Production smoke test passed | QA Lead
25 | Production Deployment | Linear issues moved to 'Deployed to Prod' | Release Manager
Post-Release
26 | Post-Release | Master merged back to develop | Release Manager
27 | Post-Release | CLIENT_VERSIONS.md updated in crego-infra | Release Manager
28 | Post-Release | Release notes generated and shared | Release Manager
29 | Post-Release | Linear issues moved to 'Done' | Release Manager
30 | Post-Release | Release branch deleted from GitHub | Release Manager
31 | Post-Release | Retrospective notes captured (if applicable) | Dir. of Eng
Client Release (repeat per client)
32 | Client Release (repeat per client) | Client branch created: release/vX.Y.Z-clientname | Release Manager
33 | Client Release (repeat per client) | Client-specific changes applied (if any) | Developer
34 | Client Release (repeat per client) | Client staging deployment verified | DevOps
35 | Client Release (repeat per client) | Client UAT sign-off received | Release Manager
36 | Client Release (repeat per client) | Client tag created: vX.Y.Z-clientname | Release Manager
37 | Client Release (repeat per client) | Client production deployed and verified | DevOps
38 | Client Release (repeat per client) | CLIENT_VERSIONS.md updated for this client | Release Manager
39 | Client Release (repeat per client) | Client-specific release notes shared | Release Manager
Status Values:
Not Started
In Progress
Done
Blocked
N/A

## Client Versions
CLIENT VERSION TRACKER — Update after every production deployment
Client | Current Version | Last Deployed | Environment | Pending Version | Notes
Shared (Internal) | v2.2.0 | 2026-02-10 | prod | — | Latest release
Vayana | v1.2.4-clienta | 2026-02-05 | client-prod | v1.3.0-clienta | UAT in progress
BCPL | v1.3.0-clientb | 2026-02-12 | client-prod | — | Up to date