## Release Overview
CREGO v2.3.0 RELEASE PLAN
Scoped from Cycle 160 (Feb 16–22, 2026)
Release Version | v2.3.0
Previous Release | v2.2.0 (Released: 15 Feb 2026)
Current Cycle | Cycle 160 (Feb 16–22, 2026)
Target Release Branch Cut | 28 Feb 2026 (end of Cycle 161)
Target UAT Start | 1 Mar 2026
Target Prod Deploy | 7 Mar 2026
Release Manager | (TBD)
Repos | crego-omni, crego-web, crego-flow, crego-infra
Release Type | Feature Release
CYCLE 160 SUMMARY
Total Issues | 93
Completed (Released + Pending Release) | 43 issues (58 pts)
In QA | 16 issues
In UAT | 6 issues
In PR Review | 3 issues
Still in Development | 13 issues
In Todo | 8 issues
Cancelled | 2 issues
KEY RELEASE THEMES
# | Theme | Key Issues | Status
1 | User Management & Permissions | CRE-4947, 4948, 4908, 4917, 4909, 4891, 4902, 4938, 4890 | Mostly in Pending Release / QA
2 | GL Enhancements | CRE-4831 (8pts), 4969, 4936, 4964, 4876 | QA / Development — high risk
3 | Invoices & SCF Module | CRE-4822, 4924, 4925, 4926, 4927, 4868 | Mixed QA / PR Review
4 | EOD & Workflow | CRE-4737, 4879, 4825, 4769, 4944 | Pending Release / QA
5 | Foreclosure & Transactions | CRE-4815, 4949, 4955, 4957, 4880, 4816, 4878 | Mixed — urgent bugs in QA
6 | Platform Stability & VAPT | CRE-4912, 4736, 4891, 4896, 4885 | Pending Release / Development
7 | Vayana & Client-Specific | CRE-4649, 4811, 4970, 4831, 4530 | UAT / QA — external dependencies
8 | DevOps & Infra | CRE-4745, 4871, 4885, 4932, 4933, 4934 | Development / Todo

## Issue Tracker
Issue ID | Title | Status | Priority | Assignee | Repo | Type | Estimate | Risk | Notes
Pending Release (37 issues — merged to develop, awaiting release)
CRE-4969 | GL Mapping disable status bug | Pending Release | Urgent | Somya Jain | crego-omni | bug | - | Low
CRE-4945 | Store info not computed for runners | Pending Release | Urgent | Amit Sharma | crego-flow | bug | 1 | Low
CRE-4973 | Pass db_alias to OmniApiClient | Pending Release | Urgent | Amit Sharma | crego-flow | bug | 1 | Low
CRE-4970 | Vayana 100 document limit | Pending Release | Urgent | Hiten Kakwani | crego-omni | hotfix | - | Low
CRE-4947 | Module permission enforcement | Pending Release | Urgent | Somya Jain | crego-web | bug | - | Low
CRE-4815 | Loan foreclosure Preview | Pending Release | Urgent | garima.a | crego-omni | feature | 2 | Low
CRE-4902 | hasRole superuser check | Pending Release | Urgent | Raj Ankur | crego-web | hotfix | 1 | Low
CRE-4937 | app_settings in Branding | Pending Release | Urgent | Raj Ankur | crego-web | feature | - | Low
CRE-4942 | app_settings in settings/auth init | Pending Release | Urgent | Raj Ankur | crego-omni | improvement | 1 | Low
CRE-4908 | Permission group codename fix | Pending Release | Urgent | Somya Jain | crego-omni | bug | - | Low
CRE-4939 | Module redirect permission error | Pending Release | Urgent | Somya Jain | crego-web | bug | - | Low
CRE-4930 | Aspire payout processing 500 | Pending Release | Urgent | garima.a | crego-omni | bug | 1 | Low
CRE-4917 | Permission action denied fix | Pending Release | Urgent | Somya Jain | crego-omni | bug | 2 | Low
CRE-4649 | Vayana Reports Requirements | Pending Release | Urgent | Somya Jain | crego-omni | hotfix | 2 | Low
CRE-4814 | Loan config import fix | Pending Release | Urgent | Somya Jain | crego-omni | bug | 1 | Low
CRE-4880 | Tax input in restructuring | Pending Release | Urgent | Somya Jain | crego-omni | feature | 1 | Low
CRE-4912 | API issues VAPT | Pending Release | Urgent | Abhishek Sharma | crego-omni | chore | 1 | Low
CRE-4962 | Fix profile tabs ordering | Pending Release | High | Nikhil Sharma | crego-web | hotfix | 1 | Low
CRE-4891 | Fix login_settings TypeError | Pending Release | High | Somya Jain | crego-omni | bug | 2 | Low
CRE-4938 | Update sidebar module permissions | Pending Release | High | Somya Jain | crego-web | feature | 1 | Low
CRE-4909 | User delete not working | Pending Release | High | Somya Jain | crego-omni | bug | 1 | Low
CRE-4822 | Invoice module errors | Pending Release | High | Somya Jain | crego-omni | bug | 1 | Low
CRE-4897 | User management UI errors | Pending Release | High | Gautam Singla | crego-web | bug | - | Low
CRE-4910 | Backend error format fix | Pending Release | High | garima.a | crego-omni | bug | - | Low
CRE-4919 | Wrong fee and tax calculation | Pending Release | High | Somya Jain | crego-omni | bug | - | Low
CRE-4906 | Group account loan creation error | Pending Release | High | Somya Jain | crego-omni | hotfix | - | Low
CRE-4737 | EOD Config & Workflow Mgmt | Pending Release | High | garima.a | crego-omni | feature | 4 | Low
CRE-4907 | Loan approved amount validation | Pending Release | High | Somya Jain | crego-omni | bug | - | Low
CRE-4927 | Invoice/PO/Drawdown overview tab | Pending Release | Medium | Somya Jain | crego-web | feature | 1 | Low
CRE-4914 | Runner ID undefined in URL | Pending Release | Medium | garima.a | crego-omni | bug | 1 | Low
CRE-4892 | System date blank loading state | Pending Release | Medium | garima.a | crego-web | bug | - | Low
CRE-4530 | CDMS Requirements | Pending Release | Medium | Somya Jain | crego-omni | hotfix | 2 | Low
CRE-4313 | Freeze header row & action column | Pending Release | Low | garima.a | crego-web | feature | 2 | Low
CRE-4887 | Remove schedule number from program | Pending Release | Low | garima.a | crego-web | improvement | 1 | Low
CRE-4932 | Github Cleanup | Pending Release | - | Gautam Singla | crego-web | chore | - | Low
CRE-4934 | Setup preview deploy for PRs | Pending Release | - | Gautam Singla | crego-web | chore | - | Low
CRE-4933 | Deploy preview using S3 | Pending Release | - | Gautam Singla | crego-web | chore | - | Low
Released (6 issues — already deployed)
CRE-3707 | Partners, Agents & Customer login | Released | Urgent | Somya Jain | crego-omni | feature | 4 | Low | Release blocker cleared
CRE-4959 | BCPL PROD Storage | Released | Urgent | Arjit Agnihotri | crego-omni | chore | - | Low
CRE-4916 | Solfin Preprod Setup | Released | Urgent | Pradeep | crego-infra | chore | - | Low
CRE-4895 | Gunicorn startup crash ModuleNotFoundError | Released | High | Abhishek Sharma | crego-omni | bug | - | Low
CRE-4629 | Report → Audit Report | Released | High | Abhishek Sharma | crego-omni | feature | 4 | Low
CRE-4953 | Salary Slip PDF extraction | Released | - | Daman Kohli | crego-ai | feature | - | Low
UAT (6 issues — awaiting user acceptance)
CRE-4901 | Solfin Prod Login Issue | UAT | Urgent | Arjit Agnihotri | crego-omni | bug | - | Medium | Client-specific
CRE-4811 | Vayana Colending Issues | UAT | Urgent | Somya Jain | crego-omni | bug | 4 | High | Needs Vayana sign-off
CRE-4921 | Adani write-off sample | UAT | Urgent | Pankaj Singh | crego-omni | feature | - | Medium | Client testing
CRE-4946 | Scope inheritance MODEL_SCOPING | UAT | Urgent | Somya Jain | crego-omni | bug | 1 | Low
CRE-4920 | Basic Home BRE API and UI | UAT | High | Amit Sharma | crego-omni | feature | - | Medium
CRE-4772 | Credflow Requirement APIs | UAT | Medium | Pankaj Singh | crego-omni | feature | 2 | Low
QA (16 issues — testing in progress)
CRE-4965 | GL Account Excel import/export broken | QA | Urgent | garima.a | crego-omni | bug | - | Medium
CRE-4949 | Foreclosure negative outstanding | QA | Urgent | garima.a | crego-omni | bug | - | Medium | Critical bug
CRE-4957 | Outstanding not zero after repayment | QA | Urgent | garima.a | crego-omni | bug | - | Medium | Critical bug
CRE-4948 | Bulk Permission not working | QA | Urgent | Somya Jain | crego-omni | bug | - | Low
CRE-4876 | Accounting on component category | QA | Urgent | garima.a | crego-omni | feature | 2 | Low
CRE-4825 | Runner list API performance 2-3x | QA | Urgent | Arjit | crego-flow | improvement | 1 | Low
CRE-4831 | GL Setup Aerem, Adani & Vayana | QA | Urgent | Somya Jain | crego-omni | feature | 8 | High | Largest item — complex integration
CRE-4769 | Schedule Snapshot in Transaction audit | QA | Urgent | garima.a | crego-omni | feature | 1 | Low
CRE-4924 | Hierarchical API for program partners | QA | High | priyam.j | crego-omni | feature | - | Low
CRE-4904 | Superuser approval actions | QA | High | Raj Ankur | crego-flow | improvement | - | Low
CRE-4944 | 500 Error synchronous EOD | QA | High | garima.a | crego-omni | bug | - | Medium
CRE-4871 | Client release tagging | QA | Medium | Pradeep | crego-infra | improvement | 2 | Low
CRE-4890 | Group permissions auto-add | QA | Medium | Somya Jain | crego-omni | bug | - | Low
CRE-4925 | Enhance program partner inputs invoices | QA | Medium | Somya Jain | crego-web | feature | - | Low
CRE-4686 | GL → Tally Integration | QA | Medium | Hiten Kakwani | crego-omni | feature | 4 | Medium | Complex integration test
CRE-4941 | EntityInfo component clean-up | QA | - | sidharth.k | crego-web | tech-debt | 1 | Low
PR Review (3 issues — awaiting merge)
CRE-4868 | Check anchor in Program partner | PR Review | Urgent | sidharth.k | crego-web | feature | 1 | Low | Archived — verify still needed
CRE-4964 | Remove balance column GL Account | PR Review | High | Harshita Rajpal | crego-omni | bug | - | Low
CRE-4926 | Integrate all_partners API invoice | PR Review | Medium | Somya Jain | crego-web | feature | 2 | Low
Development (13 issues — still in progress)
CRE-4967 | BCPL Prod DA Migration | Development | Urgent | Abhishek Sharma | crego-omni | hotfix | - | Medium | BCPL client
CRE-4885 | LOG_FORMAT=json revert | Development | Urgent | devsecops-read | crego-infra | chore | 1 | Low | Config change
CRE-4955 | Skip Pre-EMI adding instead of skip | Development | Urgent | Ashutosh Sharma | crego-omni | bug | - | Medium | Must fix before release
CRE-4879 | System txn date auto-update | Development | Urgent | Arun Kumar | crego-omni | bug | 1 | Medium
CRE-4875 | RPS Upload V2 (ZetApp) | Development | Urgent | Ashutosh Sharma | crego-omni | feature | 2 | Medium
CRE-4956 | Error in User assignment | Development | High | Harshita Rajpal | crego-web | bug | - | Medium
CRE-4745 | Optimise GCP dev and preprod | Development | High | Pradeep | crego-infra | improvement | 2 | Low | Overdue
CRE-4958 | Setup Sentry all services | Development | Medium | Abhishek Sharma | crego-web | feature | - | Medium | Stretch goal
CRE-4936 | ContactBank in GL Account | Development | Medium | sidharth.k | crego-web | improvement | - | Medium
CRE-4918 | Unable to edit payment form | Development | Medium | Nikhil Sharma | crego-web | bug | - | Medium
CRE-4874 | Document Intelligence & Analysis | Development | Medium | swastik.g | crego-ai | feature | 4 | Medium | AI module — stretch
CRE-4816 | Fees error | Development | Medium | Ashutosh Sharma | crego-omni | bug | 2 | Medium
CRE-4896 | CI Coverage failing | Development | Medium | Abhishek Sharma | crego-omni | chore | - | Low
Todo (8 issues — not started)
CRE-4963 | Argocd preprod git connection | Todo | Urgent | devsecops-read | crego-infra | bug | - | Medium
CRE-4977 | Client release for web services | Todo | Urgent | devsecops-read | crego-web | chore | - | Low
CRE-4960 | Solfin v2 deployment | Todo | Urgent | devsecops-read | crego-infra | chore | - | Medium
CRE-4899 | Workflow graph: use run_eod | Todo | Urgent | Hiten Kakwani | crego-omni | improvement | - | Low | Archived
CRE-4922 | Runners listing slow in v2 | Todo | Urgent | Amit Sharma | crego-flow | bug | 2 | Low | Archived
CRE-4923 | Increase aws-dev & prod MongoDB | Todo | High | Pradeep | crego-infra | chore | - | Medium
CRE-4889 | Multi-tranche edge cases | Todo | High | Ashutosh Sharma | crego-omni | bug | - | Medium
CRE-4714 | Realtime Outstanding & DPD at Schedule | Todo | High | Arun Kumar | crego-omni | feature | 2 | Low | Archived
STATUS SUMMARY
Pending Release | 37
Released | 6
UAT | 6
QA | 16
PR Review | 3
Development | 13
Todo | 8
TOTAL | 89

## Release Checklist
RELEASE CHECKLIST — v2.3.0
Release Date: | Target 7 Mar 2026
Release Manager: | (TBD)
Phase | # | Task | Owner | Status | Notes
PRE-RELEASE
Pre-Release | 1 | All PRs merged to develop | Dev Leads | Pending
Pre-Release | 2 | All QA items passed on develop | QA Team | Pending
Pre-Release | 3 | Release blocker issues resolved | Release Manager | Pending
Pre-Release | 4 | Security/VAPT scan passed | DevSecOps | Pending
Pre-Release | 5 | Performance baseline captured | Backend Lead | Pending
Pre-Release | 6 | Release notes drafted | PM / Release Manager | Pending
CUT RELEASE BRANCH
Cut Release Branch | 7 | Create release/v2.3.0 from develop | Release Manager | Pending | All 4 repos
Cut Release Branch | 8 | Tag release branch | Release Manager | Pending
Cut Release Branch | 9 | Deploy to pre-prod | DevSecOps | Pending
Cut Release Branch | 10 | Smoke tests on pre-prod | QA Team | Pending
Cut Release Branch | 11 | Notify teams of branch cut | Release Manager | Pending
PRE-PROD TESTING
Pre-prod Testing | 12 | Functional testing | QA Team | Pending
Pre-prod Testing | 13 | Regression testing | QA Team | Pending
Pre-prod Testing | 14 | Performance testing | Backend Lead | Pending
Pre-prod Testing | 15 | Data migration verification | Backend Lead | Pending
Pre-prod Testing | 16 | QA sign-off | QA Lead | Pending
UAT
UAT | 17 | Schedule UAT with stakeholders | PM / Release Manager | Pending
UAT | 18 | Execute UAT test cases | PM / QA | Pending
UAT | 19 | Product sign-off | Product Manager | Pending
PRODUCTION DEPLOY
Production Deploy | 20 | Final review meeting | All Leads | Pending
Production Deploy | 21 | Merge release → master/main | Release Manager | Pending | All 4 repos
Production Deploy | 22 | Create tag v2.3.0 | Release Manager | Pending
Production Deploy | 23 | Deploy to production | DevSecOps | Pending
Production Deploy | 24 | Smoke tests on production | QA Team | Pending
POST-RELEASE
Post-Release | 25 | Merge master/main → develop | Release Manager | Pending | All 4 repos
Post-Release | 26 | Publish release notes | PM | Pending
Post-Release | 27 | Monitor production (24h) | DevSecOps + Backend | Pending
Post-Release | 28 | Release retrospective | Release Manager | Pending

## Timeline
v2.3.0 RELEASE TIMELINE
Week | Dates | Phase | Key Activities | Owner | Status
Cycle 160 (Current) | Feb 16–22 | Close Cycle | Complete in-flight Dev & PR merges; clear QA backlog (16 items); UAT sign-offs (6 items); release blocker CRE-4649 closed | All | In Progress
Cycle 161 | Feb 23–28 | Stabilize & Branch Cut | Merge remaining PRs; QA pass on all cycle 160 items; cut release/v2.3.0 from develop (Feb 28); deploy to pre-prod | Release Mgr + DevSecOps | Pending
Week of Mar 2 | Mar 2–6 | Pre-prod Testing | Functional & regression testing on pre-prod; performance baseline; fix any release blockers found | QA + Dev Leads | Pending
Week of Mar 9 | Mar 9–13 | UAT | UAT with product & stakeholders; Vayana UAT (CRE-4811); client-specific testing; product sign-off | PM + QA | Pending
Target Deploy | Mar 14 | Production Deploy | Merge to master/main; tag v2.3.0; deploy; smoke tests; monitor 24h | Release Mgr + DevSecOps | Pending
Buffer | Mar 16+ | Contingency | Buffer for slippage, late UAT findings, or hotfix cherry-picks | All | Pending

## Risk Register
v2.3.0 RISK REGISTER
Risk ID | Description | Likelihood | Impact | Mitigation | Owner
R1 | GL Setup (CRE-4831) is 8pts in QA — largest single item. Complex multi-client GL config may surface integration issues late. | Medium | High | Early QA focus; dedicated QA slot; Hiten supports Somya on GL testing | Hiten / Somya
R2 | 16 issues still in QA — garima.a has 8 of them. QA bottleneck may delay release branch cut. | High | High | garima.a prioritizes urgent bugs first (CRE-4949, 4957, 4965); Somya takes non-critical items | garima.a / Somya
R3 | 13 issues still in Development — may not all make branch cut on Feb 28. | High | Medium | Strict scope cut: only urgent bugs (CRE-4955, 4879) must make it; stretch goals (Sentry, AI) defer to v2.4.0 | Abhishek
R4 | Vayana UAT (CRE-4811, 4pts) depends on external client sign-off. Colending issues require Vayana coordination. | Medium | High | Schedule UAT early this week; parallel-track with other UAT items; escalate if no response by Wed | Pankaj / Somya
R5 | Critical transaction bugs in QA — foreclosure negative outstanding (CRE-4949), repayment not zeroing (CRE-4957). If not fixed, release blocker. | Medium | High | garima.a + Ashutosh pair on root cause; escalate to Abhishek if not resolved by mid-week | garima.a / Ashutosh
R6 | Infra items (ArgoCD git connection, Solfin deployment, GCP optimization) in Todo/Development — may delay pre-prod deploy. | Medium | Medium | devsecops-read prioritizes ArgoCD fix (CRE-4963) first; Pradeep focuses on GCP optimization | Pradeep / devsecops
R7 | Permission module had massive churn (15+ issues). Regression risk is high even though most are in Pending Release. | Medium | High | Dedicated regression testing on permissions module during pre-prod phase | Somya / QA