## Overview
Crego — Target Architecture Gaps & Remediation Backlog
Closing the gap from the current 'as-observed' prod architecture to the hardened target (single-tenant client cloud + multi-tenant shared cloud).
Scope | Production only. Two target shapes: Single-Tenant (Client Cloud Deployed, cloud-agnostic) and Multi-Tenant (Crego Shared Cloud, GCP, namespace-per-tenant).
Source | Derived from architecture-overview.svg & network-architecture.svg (as observed 2026-05-05). Every warning/✗ in those diagrams is captured below as a gap to fix.
How to use | Sort by Priority then Severity. P0 items are security blockers for any prod hardening sign-off. 'Applies To' tells you which target(s) the fix is needed for.
Severity key | Critical = exploitable / data-loss / no-recovery · High = standards/compliance or resilience gap · Medium = hygiene / operability
Priority key | P0 = do first (security blocker) · P1 = required for target sign-off · P2 = hardening / nice-to-have
Effort key | S = < 1 sprint · M = 1-2 sprints · L = multi-sprint / cross-team
Applies To key | Both = single & multi-tenant · Multi = shared-cloud only · Single = client-cloud only

## Gaps Backlog
ID | Domain | Current Gap (as observed) | Target State (to build) | Applies To | Severity | Effort | Priority
G-01 | Edge / WAF | No WAF / Cloud Armor and no rate-limit policy at the edge. | Attach managed WAF (Cloud Armor / AWS WAF / Front Door) with OWASP ruleset, per-route/per-tenant rate-limiting, bot control and DDoS protection. | Both | Critical | M | P0
G-02 | Edge / TLS | TLS via HTTP-01 only — no DNS-01, so no wildcard certs; PROD edge cert flow diverges from cert-manager. | Issue wildcard certs via cert-manager DNS-01 across all environments; unify the cert flow (no per-env divergence). | Both | High | M | P1
G-03 | Ingress | NGINX install not in GitOps; version/replicas unpinned; single replica (SPOF). | Manage the ingress/Gateway fully in GitOps with pinned version and HA replica count; remove single points of failure. | Both | High | M | P1
G-04 | Resilience | kustomize override forces replicas:1 on every Deployment in PROD — defeats HPA. | Remove the replicas:1 override; let HPA own replica count with min>=2 for APIs and web. | Both | Critical | S | P0
G-05 | Autoscaling | omni-web / flow-web have no HPA. | Add HPA to web deployments (CPU/RPS based, min>=2). | Both | Medium | S | P2
G-06 | App Security | Flower (Celery monitor) exposed without auth in repo. | Front Flower with SSO / OAuth2-proxy and restrict admin paths by IP allow-list. | Both | Critical | S | P0
G-07 | Resilience | omni-celery-beat singleton has no PDB and no leader-election. | Add leader-election lock and a PDB (maxUnavailable=0) so the scheduler never double-runs or disappears. | Both | High | S | P1
G-08 | Identity / RBAC | Single shared K8s Role 'app-reader' grants secrets+configmaps+pods to 7 SAs. | Least-privilege Role per ServiceAccount; scope secret access by name; no shared broad role. | Both | Critical | M | P0
G-09 | Pod Security | No Pod Security Admission (PSA) labels on namespaces. | Enforce PSA=restricted on all prod namespaces (and per-tenant namespaces). | Both | High | S | P1
G-10 | Pod Security | readOnlyRootFilesystem:false on api/web/worker. | Set readOnlyRootFilesystem:true and add tmpfs mounts where needed; drop ALL caps; seccomp RuntimeDefault. | Both | High | S | P1
G-11 | Network Policy | Egress NetworkPolicy still allows 0.0.0.0/0 (no DNS/HTTPS-only filter). | Default-deny egress; allow only DNS + HTTPS + managed-DB CIDRs. | Both | High | M | P1
G-12 | Network Policy | No NetworkPolicies on kube-system / argocd / keda-system / eso namespaces. | Apply default-deny + scoped NetworkPolicies to all system namespaces. | Both | Medium | M | P2
G-13 | Secrets | No secret rotation policy. | Automated rotation (<=90d) with versioned references in ESO. | Both | High | M | P1
G-14 | Secrets | No CMEK / customer-managed keys on Secret Manager, PD-SSD, Cloud SQL. | Enable CMEK envelope encryption on secret store, disks and managed DBs. | Both | High | M | P1
G-15 | Secrets | argocd-repo-secret.yaml committed with placeholder PAT in repo. | Remove secret from Git; source repo creds via ESO / sealed-secrets; rotate the exposed PAT. | Both | Critical | S | P0
G-16 | Resilience | Zero PodDisruptionBudgets anywhere. | Add PDBs to every workload to protect availability during drains/upgrades. | Both | High | S | P1
G-17 | Resilience | No podAntiAffinity / topologySpreadConstraints. | Add topology spread across zones/nodes so replicas are not co-located. | Both | Medium | S | P2
G-18 | Resilience | No startup probes; memory request << limit (OOM risk). | Add startup/liveness/readiness probes; right-size requests≈limits to avoid OOM and noisy scheduling. | Both | Medium | S | P2
G-19 | Supply Chain | Image tags mutable (short-SHA, no digest pinning). | Pin images by digest; sign with cosign; enforce via Binary Authorization / admission policy. | Both | High | M | P1
G-20 | Data Tier | In-cluster stateful services single-replica, no backup CronJob, StorageClass=standard (no snapshots). | Move all prod data to managed HA services (or HA operators) with PITR, scheduled backups and tested restore. | Both | Critical | L | P0
G-21 | Messaging | RabbitMQ still in-cluster in PROD — single replica, no HA, no PDB, no backup. | Use managed/HA message broker (CloudAMQP / Amazon MQ / RabbitMQ-HA operator); per-tenant vhost in shared cloud. | Both | Critical | M | P0
G-22 | Environment Parity | PRE diverges from PRD (PRE = local DBs, PRD = managed) — promotion surprises; PRE invalid as release gate. | Make PREPROD topology identical to PROD (managed data + same addons) so it is a valid gate. | Both | High | M | P1
G-23 | Addons | cert-manager / external-dns / KEDA disabled in PROD (addons/prod-gcp has only ESO). | Enable the full addon set in prod to match other envs (cert-manager, external-dns, KEDA, ESO). | Both | High | S | P1
G-24 | Observability | No Prometheus / Grafana / Alertmanager / PrometheusRules deployed. | Deploy full metrics stack (Prometheus, Grafana, Alertmanager, kube-state-metrics, node-exporter). | Both | High | M | P1
G-25 | Observability | Sentry DSNs empty in config; apps effectively unmonitored for errors. | Populate Sentry DSNs per service via ESO; verify error capture. | Both | Medium | S | P2
G-26 | Observability | No OpenTelemetry collector; apps not instrumented. | Deploy OTel collector and instrument apps for traces/metrics. | Both | Medium | M | P2
G-27 | Observability | No centralized logs (RSYS placeholders, no Fluent Bit / Loki / EFK). | Deploy centralized logging (Loki / EFK) with tenant labels and retention. | Both | High | M | P1
G-28 | Observability | No K8s API audit log sink; no ArgoCD audit retention. | Ship K8s audit logs to BQ/GCS/object storage + SIEM; retain ArgoCD audit history. | Both | High | M | P1
G-29 | Observability | No SLOs; no alert routing (Slack / PagerDuty). | Define SLOs (per-tenant tier in shared cloud) and wire alert routing to PagerDuty/Slack. | Both | Medium | M | P2
G-30 | GitOps | PROD auto-syncs from 'main' — no tag pinning, no manual gate. | Sync prod from immutable Git tags with a manual approval gate / sync window. | Both | Critical | S | P0
G-31 | GitOps | ArgoCD AppProject prod allows sourceRepos:['*']. | Restrict AppProject to specific source repos and destination namespaces/clusters. | Both | High | S | P1
G-32 | GitOps | No CODEOWNERS; no branch protection asserted in repo. | Add CODEOWNERS, branch protection, required reviews and signed commits. | Both | High | S | P1
G-33 | CI/CD | No conftest/OPA gate; no kubeconform/kubeval schema validation. | Add OPA/conftest policy gate + kubeconform schema validation to CI. | Both | Medium | M | P1
G-34 | CI/CD | No tfsec / checkov / terrascan IaC scan. | Add IaC security scanning (tfsec/checkov) to PR pipeline. | Both | High | S | P1
G-35 | CI/CD | No Trivy / Grype container image vulnerability scan. | Add image vulnerability scanning gate (Trivy) blocking on critical CVEs. | Both | High | S | P1
G-36 | CI/CD | No terraform plan on PR (drift undetected). | Run terraform plan on PR and post diff; require review before apply. | Both | Medium | S | P2
G-37 | CI/CD | No SBOM / signed-commit / sigstore. | Generate SBOM, sign artifacts (cosign/sigstore), enforce signed commits. | Both | Medium | M | P2
G-38 | Cluster Platform | Public control-plane endpoint with Master Authorized Networks defaulting to 0.0.0.0/0. | Make control-plane endpoint private; restrict authorized networks to admin/CI CIDRs; access via bastion/IAP. | Both | Critical | M | P0
G-39 | Cluster Platform | VPC firewall allows ALL protocols/ports inside subnet/pod/svc CIDRs. | Replace with least-privilege, port-scoped firewall rules (5432/6379/5672/27017/53/443). | Both | Critical | M | P0
G-40 | Cluster Platform | No Binary Authorization; no admission policy (Kyverno / Gatekeeper). | Deploy Kyverno/Gatekeeper policies + Binary Authorization (admit only signed, scanned images). | Both | High | M | P1
G-41 | Backup / DR | No GKE Backup / Velero / PV snapshot schedule. | Deploy Velero/GKE Backup with scheduled PV snapshots and tested restores. | Both | High | M | P1
G-42 | Backup / DR | Single region (asia-south1) — no DR / pilot-light secondary. | Stand up pilot-light secondary region (cross-region read-replica + restore runbook). | Both | High | L | P1
G-43 | IaC / Terraform | DEV/QA/PRE provisioned via bootstrap-gcp.sh (gcloud) — drift-prone, no remote state. | Provision every environment via Terraform with remote state + locking; retire bootstrap scripts. | Both | High | L | P1
G-44 | IaC / Terraform | No required_version pin in versions.tf; no tfvars examples; no documented rotation. | Pin required_version + provider versions; add tfvars examples and rotation docs. | Both | Medium | S | P2
G-45 | IaC / Terraform | No drift detection (no scheduled terraform plan). | Schedule periodic terraform plan with drift alerts. | Both | Medium | S | P2
G-46 | IaC / Terraform | IAM bindings + WI GSA/KSA bindings done in bash (fix-*.sh), not Terraform. | Move all IAM and Workload Identity bindings into Terraform. | Both | Medium | M | P2
G-47 | Network Security | No VPC Service Controls perimeter. | Establish VPC-SC perimeter around managed-service projects to block data exfiltration. | Both | High | M | P1
G-48 | Network | Cloud NAT uses AUTO_ONLY IP — outbound IP can change; partner IP allow-lists break. | Reserve static NAT IP(s) for stable egress; enable NAT logging. | Both | Medium | S | P2
G-49 | Multi-tenancy | Three NS share one cluster with no ResourceQuota / LimitRange (noisy-neighbour risk). | Namespace-per-tenant with ResourceQuota + LimitRange + default-deny cross-namespace NetworkPolicy + per-tenant SA. | Multi | High | M | P1
G-50 | Multi-tenancy | Tenant isolation is logical-only (shared namespace) — weak blast-radius containment. | Adopt namespace-per-tenant model; deny tenant-to-tenant traffic; per-tenant secret/DB credentials. | Multi | High | M | P1
G-51 | Data Isolation | Shared DB access from any pod enables lateral movement if a pod is compromised. | Per-tenant logical DB/schema with scoped credentials; firewall + NetworkPolicy restrict DB reach to owning namespace. | Multi | High | M | P1

## Summary
Backlog Summary
Total gaps | 51
Critical | 10
High | 27
Medium | 14
P0 (security blockers) | 10
P1 (target sign-off) | 28
P2 (hardening) | 13
Multi-tenant-specific | 3
Applies to both targets | 48