## Cycle 160 — Close
CYCLE 160 — Feb 16–22, 2026 ¦ CLOSE THESE THIS WEEK
35 issues ¦ Only started work (Dev/PR/QA/UAT) + light-load Todo pulls ¦ Total: ~105 pts
Issue ID | Title | Status | Priority | Assignee | Est (pts) | Target | Risk | Notes
UAT — Must Close (1 issue, 2 pts)
CRE-4649 | Vayana Reports Requirements | UAT | Urgent | Somya Jain | 2 | Close Mon/Tue | Low | RELEASE BLOCKER — already in UAT, just needs sign-off
Already Completed (1 issue — Pending Release)
CRE-3707 | Partners, Agents & Customer login | Pending Release | Urgent | Somya Jain | 3 | DONE | - | RELEASE BLOCKER cleared — in Pending Release
QA — Clear Backlog (5 issues, 11 pts)
CRE-4811 | Vayana Colending Issues | QA | Urgent | Hiten Kakwani | 3 | Close by Wed | Medium | v2.2.0 — Hiten to support QA on fixes
CRE-4769 | Schedule SnapShot in Transaction audit | QA | Urgent | garima.a | 1 | Close Mon/Tue | Low | Small scope — garima picks up immediately
CRE-4530 | CDMS Requirements | QA | Medium | Somya Jain | 2 | Close by Thu | Low | v2.2.0 — Somya knows Vayana
CRE-4686 | GL → Tally Integration | QA | Medium | Hiten Kakwani | 3 | Close by Fri | Medium | v2.2.0 — complex integration test
CRE-4772 | Credflow Requirement through APIs | QA | Medium | Pankaj Singh | 2 | Close by Fri | Low | Pankaj coordinates QA testing
PR Review — Merge by Tuesday (7 issues, 10 pts)
CRE-4814 | Loan config while importing Loan | PR Review | Urgent | Ashutosh Sharma | 1 | Merge Mon | Low | v2.2.0 bug fix — reviewer merge immediately
CRE-4815 | Loan foreclosure Preview | PR Review | Urgent | Harshita Rajpal | 2 | Merge Mon | Low | Merge → QA handoff
CRE-4879 | System transaction date auto-update | PR Review | Urgent | Nikhil Sharma | 1 | Merge Mon | Low | Bug fix — straightforward
CRE-4868 | Check anchor in Program partner | PR Review | Urgent | sidharth.k | 1 | Merge Mon | Low | Small validation check
CRE-4822 | INVOICE MODULE ERRORS | PR Review | High | sidharth.k | 1 | Merge Mon/Tue | Low | Bug fix
CRE-4891 | Fix login_settings config TypeError | PR Review | High | Abhishek Sharma | 2 | Merge Mon | Low | BREAKING CHANGE — careful review needed
CRE-4736 | File security scanning on upload | PR Review | Medium | Abhishek Sharma | 2 | Merge Tue | Low | VAPT security fix
Development — Urgent: Complete by Wednesday (6 issues, 10 pts)
CRE-4880 | Tax input in fees in Restructuring | Development | Urgent | Harshita Rajpal | 1 | PR by Tue | Low | v2.2.0 — small FE change
CRE-4801 | Maker Checker | Development | Urgent | Harshita Rajpal | 4 | PR by Thu | High | Large FE feature — may not fully close
CRE-4825 | Runner list API search perf 2-3x | Development | Urgent | Amit Sharma | 1 | PR by Tue | Low | DB query optimization
CRE-4872 | Cannot create invoice uploading files | Development | Urgent | sidharth.k | 1 | PR by Tue | Low | Bug fix
CRE-4885 | LOG_FORMAT=json in dev/preprod | Development | Urgent | devsecops-read | 1 | Close Tue | Low | Config change
CRE-4876 | Accounting on component category | Development | Urgent | Abhishek Sharma | 2 | PR by Wed | Low | Architecture change — Abhishek owns
Development — High: Target PR by Friday (7 issues, 17 pts)
CRE-4829 | Feature flags in Settings | Development | High | Amit Sharma | 1 | PR by Thu | Low | v2.2.0 target — small scope
CRE-4737 | EOD Configuration & Workflow Mgmt | Development | High | Nikhil Sharma | 4 | PR by Fri | Medium | v2.2.0 — large FE, may carry over
CRE-4629 | Report → Audit Report | Development | High | Abhishek Sharma | 3 | PR by Fri | Medium | v2.2.0 target
CRE-4313 | Freeze Header Row & Action Column | Development | High | Gautam Singla | 2 | PR by Thu | Low | FE UX improvement
CRE-4745 | Optimise GCP dev and preprod | Development | High | Pradeep Devsecops | 2 | Close by Fri | Low | Infra cost optimization
CRE-4727 | DPD Starts from | Development | High | Ashutosh Sharma | 2 | PR by Thu | Low | BE logic change
CRE-4568 | Core rjsf for react native library | Development | High | Raj Ankur | 4 | PR by Fri | Medium | Mobile library — specialized work
Development — Medium: Continue & Close If Possible (5 issues, 14 pts)
CRE-4757 | Search not working product creation | Development | Medium | Gautam Singla | 1 | PR by Wed | Low | v2.2.0 bug fix — small
CRE-4816 | Fees error | Development | Medium | Ashutosh Sharma | 2 | PR by Fri | Low | Backend fix
CRE-4614 | Commercial CIC report | Development | Medium | priyam.j | 3 | PR by Fri | Low | Backend report generation
CRE-4786 | Notification Module Phase 1 | Development | Medium | Amit Sharma | 4 | PR by Fri | Medium | Larger scope — stretch goal
CRE-4874 | Document Intelligence & Analysis | Development | None | swastik.g | 4 | PR by Fri | Medium | AI module — continue
Todo → Pull into Cycle (4 issues, 7 pts — for under-loaded devs)
CRE-4714 | Realtime Outstanding & DPD at Schedule | Todo | High | Arun Kumar | 2 | PR by Thu | Low | Arun has 0 active items — pull in
CRE-4878 | CLM Prepayment Issue | Todo | Medium | Arun Kumar | 2 | PR by Fri | Low | Arun light — bug fix
CRE-4886 | Add PO/Invoice reference on UI | Todo | Medium | Gautam Singla | 1 | PR by Fri | Low | Gautam has capacity — small FE fix
CRE-4386 | K8s setup for client crego platform | Todo | Medium | Pradeep Devsecops | 2 | Progress by Fri | Low | Pradeep has capacity

## Cycle 161 — Backlog
CYCLE 161+ BACKLOG — Items Not Closing Next Week
Overflow Dev items (Abhishek), Todos not started, Requirements needing specs, VAPT backlog
Issue ID | Title | Status | Priority | Assignee | Est (pts) | Target | Risk | Notes
Development Overflow — Abhishek (CTO capacity exceeded, 6 issues, 25 pts)
CRE-4831 | GL Setup Aerem, Adani & Vayana | Development | High | Abhishek Sharma | 8 | Cycle 161-162 | - | Multi-client GL config — very large
CRE-4624 | Workflow/Runner Enhancements | Development | High | Abhishek Sharma | 3 | Cycle 161 | - | Vayana-specific feature
CRE-4730 | Integration Connector Module + NACH | Development | High | Abhishek Sharma | 4 | Cycle 161 | - | Integration module
CRE-3730 | IRAC handling in GL | Development | High | Abhishek Sharma | 4 | Cycle 161 | - | GL regulatory compliance
CRE-4798 | Write-off GL Handling | Development | High | Abhishek Sharma | 3 | Cycle 161 | - | GL write-off logic
CRE-4832 | Access Control Refinement | Development | Medium | Abhishek Sharma | 3 | Cycle 161 | - | RBAC enhancement
Todo — Not Starting This Week (5 issues, 11 pts)
CRE-4588 | BCPL CLM-1 Migration - Vreedhi | Todo | Urgent | Arjit Agnihotri | 3 | Cycle 161 | - | PM coordination — needs dev assignment
CRE-4260 | BCPL Reports | Todo | High | Arjit Agnihotri | 3 | Cycle 161 | - | PM coordination — needs dev assignment
CRE-4812 | Adani - Operative amount not updated | Todo | High | Ashutosh Sharma | 2 | Cycle 161 | - | Ashutosh at capacity in 160
CRE-4863 | Resource Meta in UI | Todo | Medium | Harshita Rajpal | 2 | Cycle 161 | - | Harshita at capacity in 160
CRE-4887 | Remove Schedule Number from Program | Todo | Low | Gautam Singla | 1 | Cycle 162+ | - | Low priority
Requirement — High (Need PM Specs, 5 issues, 13 pts)
CRE-4893 | Aerem Users & Roles Requirement | Requirement | High | Somya Jain | 2 | Spec → 161 | - | Fresh work — needs requirements before dev
CRE-4520 | Adhoc Line | Requirement | High | Ashutosh Sharma | 4 | Spec → 161, Dev → 162 | - | Needs PM spec first
CRE-4835 | Transaction Batching | Requirement | High | Arun Kumar | 3 | Spec → 161, Dev → 162 | - | Needs PM spec first
CRE-4842 | IDOR Vulnerability | Requirement | High | Nikhil Sharma | 2 | Spec → 161 | - | VAPT — assign to FE for web layer
CRE-4841 | Weak Ciphers | Requirement | High | Pradeep Devsecops | 2 | Spec → 161 | - | VAPT — infra TLS config
Requirement — Medium (14 issues, ~28 pts)
CRE-4651 | Transaction Preview | Requirement | Medium | Arun Kumar | 3 | Cycle 162+ | - | Feature spec needed
CRE-4163 | Audit capture in flow for changes | Requirement | Medium | Gautam Singla | 2 | Cycle 162+ | - | Flow module
CRE-4864 | Resource Meta Schema Finalisation | Requirement | Medium | Gautam Singla | 2 | Cycle 162+ | - | Schema design
CRE-4383 | All props form to use update param | Requirement | Medium | Gautam Singla | 2 | Cycle 162+ | - | FE architecture
CRE-4871 | Client release tagging | Requirement | Medium | Pradeep Devsecops | 2 | Cycle 162+ | - | CI/CD enhancement
CRE-4844 | No Rate Limit | Requirement | Medium | sidharth.k | 2 | Cycle 162+ | - | VAPT — API rate limiting
CRE-4847 | Improper Error Handling | Requirement | Medium | Amit Sharma | 2 | Cycle 162+ | - | VAPT fix
CRE-4846 | Improper Input Validation | Requirement | Medium | Nikhil Sharma | 2 | Cycle 162+ | - | VAPT fix
CRE-4843 | Sensitive Info Disclosure | Requirement | Medium | Amit Sharma | 2 | Cycle 162+ | - | VAPT fix
CRE-4851 | SWEET32 Attack | Requirement | Medium | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4849 | Lucky13 Attack | Requirement | Medium | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4845 | Vulnerable TLS Protocols | Requirement | Medium | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4850 | BEAST Attack | Requirement | Medium | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4848 | BREACH Attack | Requirement | Medium | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
Requirement — Low (10 issues, ~16 pts)
CRE-4830 | OIDC callback role/group handling | Requirement | Low | Hiten Kakwani | 3 | Cycle 162+ | - | Auth enhancement
CRE-4884 | BaseTestClass for Product/Program | Requirement | Low | Arun Kumar | 8 | Cycle 162+ | - | Testing infrastructure
CRE-4856 | Missing CSP Header | Requirement | Low | Gautam Singla | 1 | Cycle 162+ | - | VAPT — FE header
CRE-4855 | Misconfigured Cookies | Requirement | Low | sidharth.k | 1 | Cycle 162+ | - | VAPT fix
CRE-4853 | Concurrent Session | Requirement | Low | Hiten Kakwani | 2 | Cycle 162+ | - | VAPT — auth
CRE-4859 | Session Doesn't Timeout | Requirement | Low | Hiten Kakwani | BE Lead | 2 | Cycle 162+ | - | VAPT — auth
CRE-4852 | Server Version Disclosure | Requirement | Low | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4854 | Cacheable HTTPS Response | Requirement | Low | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4857 | Missing HSTS Header | Requirement | Low | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
CRE-4858 | Unwanted HTTP Methods | Requirement | Low | Pradeep Devsecops | 1 | Cycle 162+ | - | VAPT — infra
Moved from Cycle 160 — Requirement (6 issues, ~19 pts)
CRE-4510 | Slab interest T+1/T+2 handling | Requirement | High | Abhishek Sharma | 4 | Cycle 161 | - | Needs spec — was in cycle 160
CRE-4738 | Reversal & Backdated Transactions | Requirement | Medium | Abhishek Sharma | 8 | Cycle 162+ | - | Very large — needs spec
CRE-4883 | Service Fee/Huddle Fee Colending | Requirement | Medium | Abhishek Sharma | 2 | Cycle 161 | - | BCPL client
CRE-4873 | No need of program in user assignment | Requirement | None | Abhishek Sharma | 2 | Cycle 162+ | - | Needs spec
CRE-4646 | Config Validation | Requirement | None | Abhishek Sharma | 1 | Cycle 162+ | - | Needs spec
CRE-4813 | Config validation | Requirement | None | Abhishek Sharma | 2 | Cycle 162+ | - | Needs spec

## Team Capacity
TEAM CAPACITY & WORKLOAD — Cycle 160
Developer | Role | C160 Items | C160 Points | Weekly Capacity | Load % | C161 Items | C161 Points | Status | Key Focus This Week
Abhishek Sharma | CTO / Architect | 4 | 9 | 8 | 113% | 12 | 36 | Full | PR merges Mon, Accounting (Urgent), Audit Report (v2.2.0)
Harshita Rajpal | FE Developer | 3 | 7 | 8 | 88% | 1 | 2 | Good | Tax input v2.2.0, Maker Checker (Urgent), Foreclosure PR
Amit Sharma | BE Developer | 3 | 6 | 8 | 75% | 2 | 4 | Good | Runner API perf, Feature flags v2.2.0, Notification Module
Nikhil Sharma | FE Developer | 2 | 5 | 8 | 63% | 2 | 4 | Light | System txn date PR, EOD Config v2.2.0 (4pts)
Ashutosh Sharma | BE Developer | 3 | 5 | 8 | 63% | 2 | 6 | Good | Loan config PR v2.2.0, DPD, Fees error
sidharth.k | FE Developer | 3 | 3 | 8 | 38% | 2 | 3 | Light | Invoice bug fix, 2 PR merges — has spare capacity
Gautam Singla | FE Lead | 3 | 4 | 6 | 67% | 4 | 7 | Good | Freeze header, Search fix v2.2.0, PO/Invoice ref
Arun Kumar | BE Developer | 2 | 4 | 8 | 50% | 2 | 11 | Light | Realtime DPD, CLM Prepayment — has spare capacity
Raj Ankur | FE / Mobile | 1 | 4 | 8 | 50% | 0 | 0 | OK | React Native rjsf library (specialized)
priyam.j | BE Developer | 1 | 3 | 8 | 38% | 0 | 0 | Light | Commercial CIC report — has spare capacity
Hiten Kakwani | BE Lead | 2 | 6 | 6 | 100% | 2 | 5 | Full | Vayana colending QA, GL Tally QA support
Pradeep Devsecops | DevSecOps | 2 | 4 | 6 | 67% | 8 | 10 | Good | GCP optimization, K8s client setup
devsecops-read | DevSecOps | 1 | 1 | 4 | 25% | 0 | 0 | Light | LOG_FORMAT=json config
swastik.g | AI/ML Engineer | 1 | 4 | 8 | 50% | 0 | 0 | OK | Document Intelligence module (specialized)
Somya Jain | QA Engineer | 2 | 4 | 8 | 50% | 1 | 2 | Good | Vayana UAT (release blocker) + CDMS QA. CRE-3707 done!
garima.a | QA Engineer | 1 | 1 | 8 | 13% | 0 | 0 | Very Light | Schedule snapshot — can pick up more QA work
Pankaj Singh | PM | 1 | 2 | - | - | 0 | 0 | - | Credflow API QA coordination
Arjit Agnihotri | PM | 0 | 0 | - | - | 2 | 6 | - | BCPL items deferred to 161 — needs dev pairing
TOTALS |  | 35 | ~105 pts
KEY OBSERVATIONS:
1. CRE-3707 (Partner login) is DONE — moved to Pending Release. One release blocker cleared!
2. CRE-4893 (Aerem Users) moved to Requirement in cycle 161 — fresh work, needs specs first.
3. Somya now at 50% (2 items, 4pts) — much more manageable. garima.a still very light (1pt).
4. sidharth.k (3pts), Arun (4pts), priyam.j (3pts) have spare capacity — can absorb overflow.
5. Abhishek has 25pts of Development overflow in cycle 161 — GL module work needs delegation strategy.
6. Nikhil's EOD Config (4pts) is the largest FE item — risk of not closing if blockers emerge.
7. Remaining release blocker: CRE-4649 (Vayana Reports UAT) — must close Mon/Tue.
8. VAPT items (17 issues) all in Requirement state → assigned to relevant devs for cycle 161.