## Overview
Crego — Consolidated Infrastructure Gap Register
Detailed remediation register (your upload) merged with the single-/multi-tenant target work. Solution + Sprint preserved; 'Applies To' and tenancy-specific gaps added.
Total gaps | 58 (52 from uploaded register + 4 tenancy additions G-53..G-56 + 2 dev/qa env-conflict additions G-57..G-58)
Source — detail | Infra Gaps.xlsx (Gap Register) — concrete Solution steps + Sprint sequencing
Source — tenancy | target-state diagrams (single-tenant client cloud · multi-tenant shared cloud, namespace-per-tenant)
Severity | C — Critical (block / audit fail, Day-0) · H — High (sec/reliability, this quarter) · M — Medium (hardening) · L — Low (housekeeping)
Sprint | Day-0 = before next deploy · Sprint 1-3 = 2-week increments · Backlog = time-permitting
Applies To | Both = single & multi-tenant · Multi-tenant = shared-cloud only · Single-tenant = client-cloud only
Tabs | Gap Register (sortable/filterable) · Summary (counts) · Legend

## Gap Register
# | Area | Gap / Flag | Severity | Applies To | Sprint | Status / Note | Solution
G-01 | Edge & TLS | PRD has no WAF / Cloud Armor / rate-limit policy | H — High | Both | Sprint 2 | Required | Attach a Cloud Armor SecurityPolicy to the Gateway via GCPBackendPolicy. Start with OWASP preconfigured rule sets (xss-stable, sqli-stable) in preview for 1-2 weeks, then enforce. Add per-IP rate-limit (e.g. 600 req/min).
G-02 | Edge & TLS | cert-manager uses HTTP-01 only — no wildcard certs; LE rate-limit risk per tenant | H — High | Both | Sprint 1 | Required | Add a dns01 solver against Cloud DNS using a dedicated GSA bound via Workload Identity to the cert-manager SA. Issue one wildcard *.crego.app per env. Keep http01 as fallback.
G-03 | Edge & TLS | NGINX ingress not in GitOps (replicas/version unpinned, default = 1 replica) | H — High | Both | Sprint 1 | Required | Create addons/{env}/nginx-ingress/ ArgoCD Application pointing at chart ingress-nginx with pinned chart version, controller.replicaCount: 2, PDB minAvailable:1, explicit resources.requests, topologySpreadConstraints across zones. Remove the helm install step from bootstrap-gcp.sh.
G-04 | App tier | PRD kustomization overrides replicas: 1 for every Deployment, defeating HPA | C — Critical | Both | Day-0 | Required | Delete replicas patches in overlays/prod-gcp/kustomization.yaml. Set spec.replicas >= 2 in base Deployment so HPA minReplicas: 2 is the floor. Add replicas to ignoreDifferences in the ArgoCD Application so HPA changes do not reconcile-thrash.
G-05 | App tier | omni-web / flow-web / flower have no HPA | M — Medium | Both | Backlog | Required | Add HPAs (CPU 70%, min 2, max 4) for the web Deployments. Flower can stay at replicas:1 but needs auth (see #7).
G-06 | App tier | omni-celery-beat singleton: no PDB, no leader-election | H — High | Both | Backlog | Required | Set spec.replicas: 1 + strategy.type: Recreate to avoid double-beat overlap; add PodDisruptionBudget minAvailable:0 / maxUnavailable:1 so it can drain. Long-term: switch to celery-beat with RedBeatScheduler (Redis lock) and run replicas: 2.
G-07 | App tier | Flower exposed without ingress auth annotation in repo | H — High | Both | Backlog | Already there docker file of flower | Add nginx ingress annotation nginx.ingress.kubernetes.io/auth-type: basic + auth-secret referencing an ESO-synced htpasswd, OR front it with IAP. Deny external access entirely in PRD (internal-only).
G-08 | Identity / RBAC / Pod security | Shared K8s Role app-reader grants secrets+configmaps+pods to 7 SAs | H — High | Both | Sprint 1 | Required | Split into per-app Roles. Drop the secrets verb where the app reads its env from the ESO-projected app-env Secret (mounted, not API-fetched). Keep configmaps only where actually needed.
G-09 | Identity / RBAC / Pod security | ArgoCD prod-project allows sourceRepos: ['*'] | C — Critical | Both | Day-0 | Required | In cluster/bootstrap/app-projects.yaml set sourceRepos to ['https://github.com/crego-tech/crego-infra.git'] and destinations to the prod cluster + namespace only. Same hardening for clusterResourceWhitelist / namespaceResourceWhitelist.
G-10 | Identity / RBAC / Pod security | No Pod Security Admission labels on namespaces | H — High | Both | Sprint 2 | Required | Label namespaces: pod-security.kubernetes.io/enforce=baseline, audit=restricted, warn=restricted for DEV/QA/PRE; enforce=restricted for PRD. Add to base/{env}/namespace.yaml.
G-11 | Identity / RBAC / Pod security | readOnlyRootFilesystem: false on api/web/worker | H — High | Both | Sprint 1 | TBD | Set securityContext.readOnlyRootFilesystem: true on every app container; add emptyDir volumes for /tmp, /var/run, plus Django/Python XDG_CACHE_HOME. Roll out env-by-env (DEV -> PRE -> PRD).
G-12 | Network policy | Egress 0.0.0.0/0 still open (no DNS/HTTPS-only filter) | H — High | Both | Sprint 3 | TBD | Replace with: allow kube-dns UDP/TCP 53; allow 443/tcp to resolved CIDRs of GSM, Cloud SQL private range, Sentry, license endpoint, S3/GCS for backups. Use egress rules with to.ipBlock and document the allow-list in base/networkpolicy.yaml comments.
G-13 | Network policy | No NPs on kube-system / argocd / keda-system / external-secrets | H — High | Both | Sprint 3 | TBD | Add a default-deny-all NP per system namespace, then explicit allows: ArgoCD <-> git/Helm/cluster API, KEDA <-> K8s API + RabbitMQ, ESO <-> GSM (private Google access), kube-system <-> cluster CIDR.
G-14 | Secrets pipeline | No secret rotation policy | H — High | Both | Sprint 2 |  | Enable GSM secret versioning + a Cloud Scheduler job that rotates DB password / JWT signing key monthly via a small Cloud Run handler. ESO refreshInterval: 1h with creationPolicy: Owner picks it up. Document rotation cadence in docs/runbooks/secret-rotation.md.
G-15 | Secrets pipeline | No CMEK on GSM / PD-SSD / Cloud SQL | H — High | Both | Sprint 2 |  | Provision regional KMS keyring crego-{env}-keyring with key app-key. In Terraform: google_secret_manager_secret.encryption_config.kms_key_name, google_compute_disk.kms_key_self_link, google_sql_database_instance.encryption_key_name.
G-16 | Secrets pipeline | argocd-repo-secret.yaml has placeholder PAT in repo (likely real value previously committed) | C — Critical | Both | Day-0 |  | Delete the file. Recreate the repo Secret in-cluster via ESO sourcing from a GSM key argocd-github-pat (sealed at bootstrap). Move to a deploy-key per env if possible (read-only, repo-scoped). ROTATE THE PAT NOW since the placeholder implies a real value was committed earlier.
G-17 | Resilience (cluster-wide) | Zero PodDisruptionBudgets defined anywhere | C — Critical | Both | Day-0 |  | Generate one PDB per Deployment via a Kustomize component. minAvailable:1 for any Deployment with replicas >= 2; maxUnavailable:1 for singletons that tolerate brief downtime.
G-18 | Resilience (cluster-wide) | No podAntiAffinity / topologySpreadConstraints | C — Critical | Both | Sprint 1 |  | Add to base Deployment template: topologySpreadConstraints with maxSkew:1, topologyKey:topology.kubernetes.io/zone, whenUnsatisfiable:ScheduleAnyway. Plus podAntiAffinity preferredDuringSchedulingIgnoredDuringExecution on app.kubernetes.io/name.
G-19 | Resilience (cluster-wide) | No startup probes | M — Medium | Both | Backlog |  | Add startupProbe (httpGet /health, failureThreshold:30, periodSeconds:5) to api/web. Lets you keep aggressive livenessProbe without false kills on slow Django boot.
G-20 | Resilience (cluster-wide) | Memory request << limit (omni-api 2Gi/4Gi) — OOM contention risk | M — Medium | Both | Backlog |  | Set requests.memory == limits.memory (Guaranteed QoS). Pick the steady-state P99 from a 2-week baseline once Prometheus is in (#29).
G-21 | Resilience (cluster-wide) | Image tags mutable (short-SHA, no digest pinning) | H — High | Both | Sprint 2 |  | Update scripts/bump-image.sh to resolve and write image: registry/x@sha256:... digests, not tags. Enforce via a Kyverno verifyImages policy referencing a Cosign public key.
G-22 | Data tier | In-cluster Postgres/Redis/Mongo: single replica, no backup CronJob, StorageClass=standard | H — High | Both | Sprint 2 |  | DEV is fine. For QA/PRE: switch StorageClass to pd-balanced, add a CronJob running pg_dump/mongodump to a GCS bucket nightly with 14-day retention; also enable VolumeSnapshotClass + a daily VolumeSnapshot.
G-23 | Data tier | PRE diverges from PRD (uses local DBs) — promotion can surprise | H — High | Both | Sprint 2 |  | Provision Cloud SQL + Memorystore for PRE via Terraform (smaller tier). Toggle USE_EXTERNAL_POSTGRESQL=true in PRE overlay. PRE must mirror PRD topology to be useful as a release gate.
G-24 | Data tier | RabbitMQ in-cluster in PRD — single replica, no HA, no backup | C — Critical | Both | Sprint 1 |  | Either (a) deploy RabbitMQ Cluster Operator with 3 replicas + persistent quorum queues + PDB minAvailable:2, or (b) migrate to Cloud Pub/Sub or AmazonMQ-equivalent. (a) is the lower-risk move.
G-25 | Addons (PRD gap) | PRD missing cert-manager / external-dns / KEDA / monitoring stack (addons/prod-gcp/ has only external-secrets) | C — Critical | Both | Day-0 |  | Confirm whether genuinely absent or installed out-of-band. If absent: copy addons/preprod-gcp/{cert-manager,external-dns,keda} to addons/prod-gcp/ and add ArgoCD Applications. PRD cannot autoscale workers without KEDA, cannot auto-issue certs, and any DNS change is manual.
G-26 | GitOps (ArgoCD) | PRD auto-syncs from main — no tag pinning, no manual gate | H — High | Both | Sprint 1 |  | Change argocd-apps/prod-gcp/*.yaml targetRevision: main -> targetRevision: vX.Y.Z (semver tag). Switch syncPolicy to automated:null + syncWindows kind:deny schedule:'* * * * *' manualSync:true so promotions become explicit.
G-27 | GitOps (ArgoCD) | No CODEOWNERS / branch protection asserted in repo | H — High | Both | Sprint 1 |  | Add .github/CODEOWNERS requiring @crego-tech/platform for terraform/**, addons/**, argocd-apps/prod-gcp/**, cluster/**. In GitHub repo settings: protect main, require 2 reviews + status checks + Require linear history.
G-28 | Observability | Sentry DSNs empty in config/clients.yaml | H — High | Both | Sprint 2 |  | Create per-env Sentry projects (omni / flow); store DSN in GSM under app-env.OMNI_SENTRY_DSN / FLOW_SENTRY_DSN; remove the empty values from config/clients.yaml so the secret is the single source of truth.
G-29 | Observability | No Prometheus / Grafana / Alertmanager / PrometheusRules | C — Critical | Both | Sprint 1 |  | Deploy kube-prometheus-stack via ArgoCD in addons/{preprod,prod}-gcp/monitoring/. Use GCP Managed Prometheus as the long-term store (already enabled at the cluster) and stack components only as scrape + UI. Provision dashboards as ConfigMaps.
G-30 | Observability | No OpenTelemetry collector / no app instrumentation | H — High | Both | Sprint 2 |  | Deploy OTel Collector as a DaemonSet (receives OTLP from sidecar-less SDK in apps), exports to Cloud Trace + Cloud Logging. Add opentelemetry-instrumentation-django / -celery to omni & flow images.
G-31 | Observability | No centralised logs (RSYS_HOST/RSYS_PORT placeholders only) | C — Critical | Both | Sprint 1 |  | Cluster logs already flow to Cloud Logging via the GKE node SA roles/logging.logWriter. Add a log sink -> BigQuery dataset crego_logs_{env} with partition expiration 400 days. Drop the rsyslog plumbing — use Cloud Logging structured JSON instead.
G-32 | Observability | No K8s API audit log sink / no ArgoCD audit retention | C — Critical | Both | Sprint 1 |  | GKE: enable --logging=SYSTEM,WORKLOAD,API_SERVER (already partly on; add API_SERVER). Sink to BQ as in #31. ArgoCD: enable controller.metrics.enabled and ship argocd-server audit events through the Cloud Logging sink.
G-33 | Observability | No kube-state-metrics / node-exporter / blackbox / synthetics | H — High | Both | Sprint 2 |  | Bundled with kube-prometheus-stack (#29). Add a Probe resource per public hostname for blackbox to give an external uptime SLI.
G-34 | Observability | No SLOs / alert routing (Slack / PagerDuty) | H — High | Both | Sprint 2 |  | Define starter SLOs in addons/{env}/monitoring/slo/: omni-api availability 99.5%, flow-api availability 99.5%, celery-queue-depth p95 < 100. Wire Alertmanager -> Slack #alerts-prd + PagerDuty for severity=critical.
G-35 | CI / CD | No conftest / Open Policy Agent gate | H — High | Both | Sprint 1 |  | Add a policy/ directory with Rego rules: PSA labels present, runAsNonRoot, readOnlyRootFilesystem, resources set, image is digest-pinned, no :latest. Add 'conftest test -p policy/ apps/ overlays/ base/' to .github/workflows/validate-infra.yaml.
G-36 | CI / CD | No kubeconform / kubeval schema validation | M — Medium | Both | Backlog |  | Add 'kubeconform -summary -strict -kubernetes-version 1.30.0' against kustomize build output of every overlay in CI.
G-37 | CI / CD | No tfsec / checkov / terrascan IaC scan | H — High | Both | Sprint 2 |  | Add aquasecurity/tfsec-action to a new terraform-validate.yaml workflow on terraform/** paths; fail on HIGH+. Optionally add checkov for compliance frameworks (CIS GCP, SOC 2).
G-38 | CI / CD | No image vulnerability scan (Trivy / Grype) | H — High | Both | Sprint 2 |  | Run Trivy in the app repos (omni, flow) at build time and fail on CRITICAL. In infra repo, run a nightly Trivy scan of all images currently referenced by kustomization.yaml and post a Slack digest.
G-39 | CI / CD | No 'terraform plan' on PR (drift undetected) | H — High | Both | Sprint 1 |  | New workflow: on PR touching terraform/**, run terraform fmt -check, terraform init, terraform validate, terraform plan -no-color -out plan.bin, post the plan as a PR comment via actions/github-script.
G-40 | CI / CD | No SBOM / signed commits / Sigstore | M — Medium | Both | Sprint 2 |  | Generate SBOM with anchore/sbom-action in app build pipelines; sign images with cosign sign --keyless (uses GH OIDC) and verify in the Kyverno policy from #21.
G-41 | CI / CD | Promotion via scripts (manual SHA pin) | M — Medium | Both | Backlog |  | Replace bump-image.sh with an ArgoCD Image Updater (or Renovate) flow: PR is opened automatically when a new digest is pushed; merging promotes.
G-42 | Cluster platform / GKE | Public control-plane endpoint, MAN defaults to 0.0.0.0/0 | C — Critical | Both | Day-0 |  | In bootstrap script and Terraform: set master_authorized_networks_config to office CIDRs + a bastion IP only. Better: enable_private_endpoint=true and access via Identity-Aware Proxy (IAP) tunnel.
G-43 | Cluster platform / GKE | VPC firewall allows ALL protocols/ports inside subnet/pod/svc CIDRs | H — High | Both | Sprint 2 |  | Replace blanket allow rule with explicit allows: TCP 5432 (PG), 6379 (Redis), 5672/15672 (RabbitMQ), 27017 (Mongo), 53 UDP/TCP, 443 (control plane).
G-44 | Cluster platform / GKE | No CMEK on PD-SSD / Cloud SQL / GSM (cluster-platform restatement of #15) | H — High | Both | Backlog |  | Same key as #15. Track together to avoid duplicate KMS provisioning work.
G-45 | Cluster platform / GKE | No Binary Authorization / Kyverno / Gatekeeper admission policy | H — High | Both | Sprint 3 |  | Enable GKE Binary Authorization in enforce mode; require attestation by qa-attestor (signed in CI after tests pass) and vuln-attestor (signed by Trivy if no CRITICAL). Plus deploy Kyverno for the digest + signed-image policies (#21, #40).
G-46 | Cluster platform / GKE | No GKE Backup / Velero / PV snapshot schedule | C — Critical | Both | Sprint 3 |  | Enable GKE Backup for GKE (managed). Define a BackupPlan per cluster: daily, retain 30 days, include all namespaces. Restore drill quarterly — log evidence under crego-internal-docs/compliance/disaster-recovery/.
G-47 | Cluster platform / GKE | Single region asia-south1 — no DR / pilot-light | C — Critical | Both | Sprint 3 |  | Phase 1 (cheap): cross-region Cloud SQL read-replica in asia-south2, daily Cloud Storage cross-region backup of GKE Backup. Phase 2: pilot-light GKE in asia-south2, ArgoCD pre-staged but not synced; DNS failover via Cloud DNS health-check policies.
G-48 | Terraform / IaC | DEV / QA / PRE provisioned via bootstrap-gcp.sh — drift-prone, no remote state | H — High | Both | Sprint 3 |  | Create terraform/environments/gcp/{dev,qa1,qa2,preprod}/ mirroring prod/. Import existing resources with terraform import. Move bootstrap script to a one-time terraform apply plus a minimal 'create the GCS state bucket' pre-step.
G-49 | Terraform / IaC | No tfvars examples | M — Medium | Both | Backlog |  | Add terraform.tfvars.example per env with safe defaults; commit and exclude real terraform.tfvars via .gitignore.
G-50 | Terraform / IaC | No required_version pin in versions.tf | L — Low | Both | Backlog |  | Add terraform { required_version = '>= 1.7.0, < 2.0.0' } and pin provider versions.
G-51 | Terraform / IaC | No drift detection (no scheduled terraform plan) | H — High | Both | Sprint 3 |  | Schedule a daily terraform plan GH Actions workflow per env; post diff to Slack #infra-drift if non-empty.
G-52 | Terraform / IaC | IAM bindings for ESO / external-dns / KEDA done in bash, not Terraform; WI bindings created post-hoc by fix-external-secrets-auth.sh | M — Medium | Both | Backlog |  | Move every gcloud iam service-accounts add-iam-policy-binding call into the relevant Terraform module (google_service_account_iam_member). The fix- script's existence is itself the bug.
G-53 | Multi-tenancy | Shared cluster runs multiple tenants in one namespace — no ResourceQuota/LimitRange (noisy-neighbour) and only logical isolation. | C — Critical | Multi-tenant | Sprint 2 | Required · See prod-namespace-per-tenant-design.md | Adopt namespace-per-tenant: ArgoCD ApplicationSet generates ns tenant-<id> with ResourceQuota + LimitRange, a dedicated ServiceAccount, and scoped RBAC. Per-tenant ESO ExternalSecret (key app-prod-<tenant>).
G-54 | Multi-tenancy | No tenant-to-tenant network isolation (any pod can reach any pod across tenants). | H — High | Multi-tenant | Sprint 2 | Required · See prod-namespace-per-tenant-design.md | Default-deny NetworkPolicy in every tenant namespace; explicitly deny cross-namespace traffic; allow only same-namespace + shared ingress/egress. Add NPs on system namespaces (see #13).
G-55 | Data isolation | Shared managed DB reachable by any pod → lateral movement / cross-tenant data access if a pod is compromised. | H — High | Multi-tenant | Sprint 2 | Required · See prod-namespace-per-tenant-design.md | Per-tenant logical database/schema with row-level scoping and per-tenant DB credentials (no shared superuser). Scope reachability with VPC firewall (#43) + egress NetworkPolicy so a pod reaches only its own DB.
G-56 | Single-tenant delivery | No automated per-client provisioning for client-cloud deployments (cloud-agnostic). | M — Medium | Single-tenant | Sprint 3 | Required | Parameterize Terraform + Helm/Kustomize per client and target cloud (EKS/AKS/GKE): per-client isolated remote state, secret store, KMS key and DNS zone. Ship a one-command client-bootstrap pipeline with the same hardening baseline.
G-57 | Secrets pipeline | dev/qa1/qa2 share one cluster but each overlay defines a cluster-scoped ClusterSecretStore named cloud-sm — three ArgoCD apps contend for one object; currently masked by commenting it out of qa1/qa2 kustomizations so qa secrets auth via dev eso-sa. | C — Critical | Both | Day-0 | Required · See dev-qa-environment-isolation-design.md | Convert cloud-sm from ClusterSecretStore to a namespaced SecretStore in each overlay (dev/qa1/qa2) and flip ExternalSecret secretStoreRef.kind to SecretStore — removes the collision. Ensure each namespace has its own eso-sa + Workload Identity binding. Re-enable secret-store.yaml in qa1/qa2 kustomizations. Delete the old cluster-scoped cloud-sm only after all three namespaced stores report SecretSynced.
G-58 | Edge & TLS | dev/qa1/qa2 gateway model half-switched: qa1/qa2 carry disabled per-env Gateways (qa1-gateway/qa2-gateway on reserved static IPs crego-qa1-ip/crego-qa2-ip) while their live HTTPRoutes ride dev-gateway wildcard *.dev.crego.ai. Contradictory committed files + likely idle, billed static IPs. | H — High | Both | Sprint 1 | Required · See dev-qa-environment-isolation-design.md | Standardize on one shared non-prod Gateway (ideally in a neutral infra namespace, not dev) with from:All + wildcard cert; each env owns only its HTTPRoute. Delete dead gateway.yaml/gcpgatewaypolicy.yaml from qa1/qa2 overlays and their commented refs. Release crego-qa1-ip/crego-qa2-ip after confirming no LB references them.

## Summary
Consolidated Summary
By Severity
C — Critical | 15
H — High | 33
M — Medium | 9
L — Low | 1
Total | 58
By Sprint
Day-0 | 7
Sprint 1 | 14
Sprint 2 | 18
Sprint 3 | 8
Backlog | 11
Total | 58
By Applies To
Both | 54
Multi-tenant | 3
Single-tenant | 1
Total | 58
By Area
Observability | 7
CI / CD | 7
Cluster platform / GKE | 6
Resilience (cluster-wide) | 5
Terraform / IaC | 5
App tier | 4
Identity / RBAC / Pod security | 4
Edge & TLS | 4
Secrets pipeline | 4
Data tier | 3
Network policy | 2
GitOps (ArgoCD) | 2
Multi-tenancy | 2
Addons (PRD gap) | 1
Data isolation | 1
Single-tenant delivery | 1
Total | 58

## Legend
Legend | Unnamed: 1 | Unnamed: 2
Severity
Code | Meaning | Action timing
C — Critical | Block deployments / audit failure | Immediate (Day-0)
H — High | Significant security or reliability gap | Within current quarter
M — Medium | Hardening / hygiene improvement | Backlog, time-bound
L — Low | Nice-to-have / housekeeping | When touching the area
Sprint
Sprint | Description
Day-0 | Stop-the-bleeding — fix before next deploy
Sprint 1 | First 2-week sprint — visible compliance + reliability wins
Sprint 2 | Second sprint — hardening, scanning, observability depth
Sprint 3 | Third sprint — DR, multi-region, IaC parity
Backlog | Time-permitting hygiene; revisit each quarter
Acronyms
Acronym | Meaning
HPA | Horizontal Pod Autoscaler
KEDA | Kubernetes Event-Driven Autoscaling
PDB | Pod Disruption Budget
PSA | Pod Security Admission
WI | Workload Identity
GSA | Google Service Account
KSA | Kubernetes Service Account
ESO | External Secrets Operator
GSM | Google Secret Manager
NEG | Network Endpoint Group
NP | Network Policy
MAN | Master Authorized Networks
CMEK | Customer-Managed Encryption Keys
BA | Binary Authorization
WAF | Web Application Firewall
SLO | Service Level Objective
OTel | OpenTelemetry
OPA | Open Policy Agent
SBOM | Software Bill of Materials
PITR | Point-In-Time Recovery
DR | Disaster Recovery
HA | High Availability
IaC | Infrastructure-as-Code
PAT | Personal Access Token
IAP | Identity-Aware Proxy
LE | Let's Encrypt