## Summary
Crego Engineering — KRA Baseline Report
Period: 1 May 2026 → 18 May 2026 (18 days) · Source: Linear (Tech team) · Generated 19 May 2026
Why a baseline?
This is the first measurement against the new Developer + Team Lead KRAs. Numbers here become the starting point — the next quarterly review compares against these, and gaps in the Linear data itself tell us where to tighten the process so future quarters are easier to score.
Headline numbers
Metric | Value | Notes
Issues touched in window | 284 | Any state change in May 1–18
Issues completed (Released + Pending Release) | 75 | completedAt within window
Issues started (moved into Development) | 77 | startedAt within window
Issues cancelled in window | 6
Hotfixes completed | 1 | label:type/hotfix + completed in window
Production-escape issues (label found-in/prod) | 5 | Bugs discovered in prod
Pre-prod-escape issues (label found-in/preprod) | 14 | Bugs caught in pre-prod QA
Urgent (P0/P1) bugs touched | 24 | priority=Urgent + label:bug
Currently in Pending Release (awaiting tag) | 115 | Big release queued — TL owns this
Currently in QA / Dev / PR Review | 19 / 17 / 10 | In-flight pipeline
Stale in-flight (>14 days since startedAt, not Released) | 71 | Aging WIP — TL drumbeat
Median cycle time (startedAt → completedAt) | 4.63 days | Of issues completed in window
Avg cycle time | 10.36 days | Pulled up by long-running items
Label hygiene — fully labeled (type+repo+client) at completion | 29 / 75 (39%) | Process compliance
What stands out
• Label hygiene is at 39% — only 29 of 75 completed issues had the full set of type/* + repo/* + client/* labels. This is the cheapest KRA to fix this quarter (set up a CI check or Linear automation).
• 115 issues are sitting in Pending Release. That points to a release-tag bottleneck — once the next release ships, completed-count for this window will be understated.
• 71 issues are stale in-flight (>14 days since startedAt). TLs should run a weekly stale-WIP review.
• 1 hotfix in window (CRE-5494, Gautam) — well within the ≤2/quarter target. 5 issues carry the found-in/prod label.
• Median cycle time is 4.63 days, average is 10.36 days — the gap suggests a long tail of slow-moving issues skewing the average.

## Team Rollup vs KRAs
Team-Level Metrics Mapped to KRA Framework
Numbers are absolute counts unless noted. Targets shown are the KRA framework targets, prorated where appropriate for this 18-day window.
KRA Area | Metric | Window value | Quarterly Target | Status | Source / Definition | Trackable today? | Action
Release Delivery | Hotfixes completed (label hotfix) | 1 | ≤ 2 / quarter | OK | label:type/hotfix + completedAt | Yes | Maintain
Release Delivery | Issues stuck in 'Pending Release' (awaiting tag) | 115 | Should drain on release cut | WATCH | status:Pending Release | Yes | TL: cut next release
Team Velocity | Issues completed in window | 75 | Trend metric — establish baseline | BASELINE | completedAt in [May 1, May 19) | Yes | Set Q-target after 2 cycles
Team Velocity | Issues started in window | 77 | Roughly matches completed | BASELINE | startedAt in window | Yes | —
Team Velocity | Stale in-flight (>14d since started) | 71 | ≤ 5% of open WIP | WATCH | status in {Dev,PR,QA,Pending} + age>14d | Yes | Weekly TL stale-WIP review
Quality Oversight | Production defect escape (found-in/prod tagged) | 5 | ≤ 2 / quarter / dev | BASELINE | label:found-in/prod | Yes | Confirm assignee accuracy
Quality Oversight | Pre-prod escape (found-in/preprod) | 14 | Compare quarter-on-quarter | BASELINE | label:found-in/preprod | Yes | —
Quality Oversight | Urgent (P1) bugs touched | 24 | Compare quarter-on-quarter | BASELINE | priority=1 + label:bug | Yes | —
Process Health | Label hygiene on completed issues | 29/75 (39%) | ≥ 95% fully labeled | GAP | Has type/* + repo/* + client/* on completion | Yes | Add CI or Linear automation
Process Health | Completed issues missing required labels | 46 | ≤ 5% of completed | GAP | Inverse of above | Yes | Make labels required in QA exit
Process Health | Median cycle time (Start → Complete) | 4.63 d | ≤ 7 days (proposed) | BASELINE | startedAt → completedAt | Yes | Set after 1 quarter
Process Health | Avg cycle time | 10.36 d | Watch tail | BASELINE | Average | Yes | Investigate long-tail items
Incident & Hotfix | Post-hotfix branch sync (master→develop) | N/A | 100% | NOT TRACKED HERE | Needs git log of merge commits | Partial | Pull from GitHub next pass
People & Capability | 1:1 cadence | N/A | ≥ 1 / report / month | NOT TRACKED HERE | Calendar audit | No | Authenticate Google Calendar
Stakeholder Comms | Release notes published | N/A | 100% before tag | NOT TRACKED HERE | release-notes/ folder vs git tag | Partial | Cross-check next pass

## By Person
Per-Person Activity (Tech team, May 1–18 2026)
Role column is empty for you to assign Dev / TL / QA / DevOps. Sorted by issues completed in window (desc). Use the KRA spreadsheet to score each person against role-specific targets.
Name | Role (Dev/TL/QA/DevOps) | Touched | Started | Completed | P1 Completed | Bugs Completed | Hotfix Touched | Found-in/Prod | Fully-Labeled / Completed | Label Hygiene % | Cycle p50 (d) | Cycle Avg (d) | In QA / Dev / PR / Pending
Somya Jain |  | 41 | 7 | 16 | 8 | 7 | 3 | 2 | 11 / 16 | 69% | 12 | 13.88 | 2 / 0 / 0 / 37
abhinav.n@crego.ai |  | 22 | 11 | 13 | 9 | 3 | 0 | 0 | 6 / 13 | 46% | 5.77 | 16.47 | 4 / 0 / 1 / 16
Raj Ankur |  | 23 | 6 | 9 | 4 | 1 | 0 | 0 | 3 / 9 | 33% | 5.57 | 7.6 | 0 / 1 / 0 / 12
Abhishek Sharma |  | 35 | 4 | 7 | 3 | 6 | 0 | 0 | 1 / 7 | 14% | 6.05 | 6.05 | 0 / 1 / 0 / 7
garima.a@crego.ai |  | 25 | 10 | 7 | 1 | 6 | 0 | 0 | 5 / 7 | 71% | 3.15 | 4.37 | 6 / 0 / 0 / 19
Kushagra |  | 15 | 6 | 6 | 4 | 0 | 0 | 0 | 1 / 6 | 17% | 1.67 | 2.46 | 3 / 0 / 0 / 7
het.s@crego.ai |  | 7 | 4 | 5 | 2 | 4 | 0 | 0 | 0 / 5 | 0% | 0.94 | 2.39 | 1 / 1 / 0 / 5
Arun Kumar |  | 18 | 7 | 3 | 1 | 3 | 0 | 0 | 0 / 3 | 0% | 1.03 | 0.74 | 1 / 2 / 2 / 2
Amit Sharma |  | 11 | 5 | 3 | 2 | 1 | 0 | 0 | 0 / 3 | 0% | 0.04 | 0.04 | 0 / 0 / 3 / 4
Hiten Kakwani |  | 13 | 4 | 2 | 0 | 1 | 0 | 1 | 0 / 2 | 0% | 5.35 | 5.35 | 1 / 3 / 0 / 2
Gautam Singla |  | 24 | 3 | 1 | 0 | 0 | 1 | 1 | 1 / 1 | 100% | 71.01 | 71.01 | 0 / 1 / 2 / 1
priyam.j@crego.ai |  | 11 | 2 | 1 | 0 | 0 | 0 | 1 | 1 / 1 | 100% | 3.12 | 3.12 | 0 / 1 / 0 / 0
Pankaj Singh |  | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 0 / 1 | 0% | 11.84 | 11.84 | 1 / 0 / 0 / 1
Harshita Rajpal |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 / 1 | 0% | 37.81 | 37.81 | 0 / 1 / 0 / 1
saurav.k@crego.ai |  | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 1 / 0 / 0
Nikhil Sharma |  | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 1 / 1 / 0
swastik.g@crego.ai |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 3 / 0 / 0
Arjit Agnihotri |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 0 / 0 / 0
sidharth.k@crego.ai |  | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 1 / 1 / 0
Pradeep Devsecops |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 0 / 0 / 0
nisha@crego.ai |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 0 / 0 / 1
Shubham Singh |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 / 0 | — | — | — | 0 / 0 / 0 / 0

## Drilldowns
Issue Drill-downs — Hotfixes, Prod Escapes, Stale In-Flight
Hotfixes (label type/hotfix)
ID | Title | Status | Assignee | Priority | Labels
CRE-5576 | Make program non mandatory while creating group account | Pending Release | Somya Jain | Urgent | hotfix, vayana, crego-web
CRE-5531 | Error on Resetting Schedule After Adding Charge in Draft Stage | Pending Release | Somya Jain | Urgent | bcpl, preprod, crego-omni, hotfix, v2.7.0
CRE-5530 | [CRE-5523, CRE-5516] Cherry-pick features to master: JSONLogic ops + workbook up | Pending Release | Somya Jain | Urgent | crego-flow, hotfix, bcpl, v2.7.0
CRE-5494 |  | Released | Gautam Singla | 1 | prod, shared, crego-web, hotfix, v2.7.0
Production escapes (label found-in/prod)
ID | Title | Status | Assignee | Priority | Labels
CRE-5588 | Colending split Api's modification | Released | priyam.j@crego.ai | High | crego-omni, improvement, prod, vayana
CRE-5122 | Add an option to select lender Bank in Program | Backlog | Hiten Kakwani | High | crego-omni, feature, prod, vayana
CRE-5443 | Add Reset Password Option for Super User on UI | Pending Release | Somya Jain | High | improvement, crego-web, bcpl, prod, v2.7.0
CRE-5628 | Component Code Not Visible on UI for GL Bulk Import | Pending Release | Somya Jain | Urgent | bug, vayana, prod, crego-web
CRE-5494 |  | Released | Gautam Singla | 1 | prod, shared, crego-web, hotfix, v2.7.0
Top 15 stale in-flight (started before May 1, still Dev/PR/QA/Pending Release)
ID | Title | Status | Assignee | Started | Priority
CRE-4978 | Maker Checker Backend | Pending Release | abhinav.n@crego.ai | 2026-02-21 | Urgent
CRE-4979 | Maker Check Frontend | Pending Release | abhinav.n@crego.ai | 2026-02-21 | Urgent
CRE-4961 | Generic Form Dialog component | Pending Release | Gautam Singla | 2026-02-24 | Medium
CRE-5236 | Imp screen support Mobile responsiveness | Pending Release | Harshita Rajpal | 2026-03-24 | Low
CRE-5286 | Create a separate nav menu for settings | Pending Release | Somya Jain | 2026-03-25 | High
CRE-5310 | Update report forms to use RJSF | Pending Release | Somya Jain | 2026-03-31 | High
CRE-4609 | Case assignment matrix | PR Review | Amit Sharma | 2026-04-06 | High
CRE-5387 | Gl Enhancements BE | Pending Release | Somya Jain | 2026-04-06 | High
CRE-4520 | Feature: Adhoc Limit + Shift limit check at drawdown submit for approval | Pending Release | Somya Jain | 2026-04-08 | Urgent
CRE-5322 | Integrate Notification Rules and Template Configuration on Frontend | Pending Release | garima.a@crego.ai | 2026-04-09 | Medium
CRE-5418 | FE: Adhoc Limit | Pending Release | Somya Jain | 2026-04-10 | Urgent
CRE-5297 | Group Account should be mandatory for SCF product type. | Pending Release | abhinav.n@crego.ai | 2026-04-10 | Urgent
CRE-5402 | RPS Active bulk import errors | Pending Release | Somya Jain | 2026-04-13 | High
CRE-5429 | UCIC Search | Development | Arun Kumar | 2026-04-14 | Urgent
CRE-5445 | Change BCPL policy | Pending Release | Somya Jain | 2026-04-16 | High

## Methodology & Caveats
How these numbers were computed
Source | Linear `list_issues` API for team=Tech, filtered to issues updated on or after 2026-05-01.
Window | 1 May 2026 00:00 UTC → 19 May 2026 00:00 UTC (covers May 1–18 inclusive).
Issues completed | Issue has `completedAt` in window — i.e., transitioned to a `completed` state-type (Released or Pending Release) inside the window. Note: 'Pending Release' issues are counted as completed because they have already passed QA/PR and are only waiting for the release tag.
Hotfix completed | Has label `type/hotfix` AND `completedAt` in window.
Production defect escape | Issue has label `found-in/prod`. Includes issues created before the window that are still being worked. Assignment is to whoever currently owns the issue in Linear, which may not be the developer who introduced the bug — TL should validate before scoring.
Cycle time | (completedAt − startedAt) in days. Only computed for issues completed in window with a non-null startedAt. Median (p50) and mean reported.
Stale in-flight | Issue is in Development, PR Review, QA, or Pending Release AND startedAt is before 1 May 2026 AND age > 14 days.
Label hygiene | Issue completed in window has at least one label in each of: type/*, repo/*, client/*. Target ≥ 95%.
Role assignment | Linear does not encode Dev / TL / QA role. Roles are left blank in the By Person tab for the user to fill in based on org chart.
Known gaps in this pass | QA reject rate (QA → Development back-transitions) is NOT in this report because list_issues does not return state transition history. To compute it, we need either Linear's Insights export or a per-issue history fetch — pre-spec'd for the next iteration.
Other gaps | PR review SLA, branch/PR-naming compliance, release tag timing, and post-hotfix branch sync require GitHub access — `plugin_platform-architect_github` is connected but not yet authenticated.
Other gaps (2) | 1:1 cadence, weekly status updates, knowledge-share sessions require Google Calendar and Slack access.
Page 2 caveat | Of 282 issues in scope, the 32 with updatedAt between 1–5 May were captured with a subset of fields (id, status, labels, assignee, completedAt). Title and full description are not included for those 32 in the drill-downs.